## Project Summary
Week | Phase | Overall Status | Notes
Week 1 | Foundation & Architecture | Not Started
Week 2 | Discovery & Classification | Not Started
Week 3 | Retention Decision Engine | Not Started
Week 4 | Human Review + Audit Trail | Not Started
Week 5 | End-to-End Testing | Not Started
Week 6 | Final Demo & Documentation | Not Started

## Suhas
Week | Task/Module | Status | Priority | Start Date | End Date | Comments
Week 1 | AWS setup, IAM roles, Step Functions, Architecture diagram | In Progress | High
Week 2 | Lambda orchestration, EventBridge scheduling | Pending | High
Week 3 | Decision workflow orchestration, approval flow | Pending | High
Week 4 | Approval dashboard, notifications, monitoring | Pending | High
Week 5 | Workflow debugging and fixes | Pending | High
Week 6 | Final architecture presentation and deployment | Pending | High

## Ansh
Week | Task/Module | Status | Priority | Start Date | End Date | Comments
Week 1 | S3 buckets, sample data, DynamoDB schema | In Progress | High
Week 2 | Textract integration, metadata extraction, OpenSearch indexing | Pending | High
Week 3 | Retention evaluation Lambda, archive logic | Pending | High
Week 4 | Audit logging, CloudTrail integration | Pending | High
Week 5 | Performance testing and optimization | Pending | High
Week 6 | Final technical documentation | Pending | High

## Anvitha
Week | Task/Module | Status | Priority | Start Date | End Date | Comments
Week 1 | Retention rules, legal hold matrix, compliance docs | In Progress | High
Week 2 | Metadata validation rules, governance docs | Pending | High
Week 3 | Legal hold validation, risk scoring | Pending | High
Week 4 | Audit evidence validation, compliance testing | Pending | High
Week 5 | Compliance walkthrough and reporting | Pending | High
Week 6 | Final governance and risk presentation | Pending | High

## Risk Tracker
Risk ID | Description | Owner | Severity | Mitigation Plan | Status
R1 | Metadata inconsistency | Ansh | High | Validation rules and enrichment | Open
R2 | Legal hold misclassification | Anvitha | Critical | Manual review approval | Open
R3 | Workflow integration issues | Suhas | Medium | Incremental testing | Open

## AWS Components
Layer | AWS Service | Purpose
Storage | Amazon S3 | Document repository
Archive | S3 Glacier | Long-term archive
Workflow | AWS Step Functions | Agent orchestration
Compute | AWS Lambda | Serverless execution
Metadata | DynamoDB | Metadata storage
AI | Amazon Bedrock | AI-assisted classification
OCR | Amazon Textract | Document extraction
Search | OpenSearch | Audit and metadata search
Logging | CloudTrail + CloudWatch | Audit and monitoring